## Coria Burndown Chart Template
SPRINT #2 BURNDOWN CHART
Items
|  |  | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| 1 | As a User, I want to know my info is safe | 13 | Day 1: 2; Day 2: 2; Day 3: 5; Day 6: 4
| 2 | As a User, I want to be able to fill out information for my event so people can join it | 5 | Day 3: 5
| 3 | As a user, I want to be able to specify the location of my event | 3 | Day 4: 3
| 4 | As a user I want to see the event I have created | 5 | Day 4: 5
| 5 | As a user, I want to be able to specify the start/end time of my event | 3 | Day 4: 3
| 6 | As a user, I want to be able to see events so I can join them | 8 | Day 7: 4; Day 8: 4
| 7 | Connect login Page with Main Button Page | 3 | Day 10: 3
| 8 | Restful API | 13 | 1 | 1 | 2 | 2 | 2 | 2 |  | 3
| 9 | Deploy RESTful API to AWS isntance | 3 | Day 9: 3
| 10 | As a user, I want to be able to sign up for an account | 5 | Day 2: 5
| 11 | As a user, I want to be able to login so I can join an event | 3 | Day 2: 1; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 3
| 12 | Integrate Google Maps API into React Native Map | 7 | Day 7: 2; Day 8: 3
| 13 | As a user, I want to be able to see events near my current location on a map | 5 | bar: Day 9
| 14 | Set up Location Services that feeds the users current location to the API | 5 | bar: Day 9
| 15 | As a user, I want to be able to view my profile | 5
|  | Remaining Effort | 86 | 83 | 74 | 61 | 47 | 44 | 35 | 29 | 19 | 14 | 11
|  | Ideal Trend | 86 | 77.4 | 68.8 | 60.2 | 51.6 | 43 | 34.4 | 25.8 | 17.2 | 8.6 | 0