## Coria Burndown Chart Template
SPRINT #3 BURNDOWN CHART
Items
|  |  | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day20
| 1 | Integrate Google Maps API into React Native Map | 7 | Day 1: 4; Day 2: 3
| 2 | As a user, I want to be able to see events near my current location on a map | 5 | Day 3: 5
| 3 | Set up location services so that it feeds the user's current location to the API | 5 | Day 1: 3; Day 2: 2
| 4 | As a user, I want to be able to view my profile (Account information) | 2 | Day 19: 2
| 5 | As a user, I want to be able to join events | 3 | Day 16: 3
| 6 | As a user, I want to be able to view events I have joined and created | 3 | Day 16: 3
| 7 | As a user, I want to be able to delete events | 3 | Day 16: 3
| 8 | As a user, I want to be able to see event locations on a map | 5 | Day 3: 2; Day 4: 1; Day 5: 1; Day 6: 1
| 9 | As a user, I want to be able to see my current location on a map | 5 | Day 19: 3; Day20: 2
| 10 | As a user, I want to be able to see my current location relative to an event location on a map | 5 | bar: Day 14 to Day 18
| 11 | As a user I want to be able to place a marker to place the event's location | 5 | Day 15: 3; Day 16: 2
|  | Remaining Effort | 48 | 41 | 36 | 29 | 28 | 27 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 25 | 21 | 9 | 8 | 7 | 2 | 0
|  | Ideal Trend | 48 | 45.6 | 43.2 | 40.8 | 38.4 | 36 | 33.6 | 31.2 | 28.8 | 26.4 | 24 | 21.6 | 19.2 | 16.8 | 14.4 | 12 | 9.6 | 7.2 | 4.8 | 2.4 | 1.6875e-14