## Coria Burndown Chart Template
SPRINT #1 BURNDOWN CHART
Items
|  |  | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
| 1 | Basic UI w/ Button | 3 | Day 3: 2; Day 6: 1
| 2 | As a User, I need a login page so I can login to the app | 3 | Day 7: 1; Day 8: 2
| 3 | Vision Statement | 1 | bar: Day 1
| 4 | Connect Frontend to mLAB API to access MongoDB instance | 2 | Day 1: 2
| 5 | Set up Database | 2 | Day 1: 2
|  | Remaining Effort | 11 | 6 | 6 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0
|  | Ideal Trend | 11 | 9.9 | 8.8 | 7.7 | 6.6 | 5.5 | 4.4 | 3.3 | 2.2 | 1.1 | 1.7764e-15